Title: RACI + WWWWWH Pack (Merged) — v2 (Human‑Scannable + Handout)

How to use this page (10 seconds)

- Read the Executive Summary.

- Check which Gate you’re on; complete its 3 bullets.

- File artifacts in /docs or /artifacts as listed; record approvals in the strip.

Executive Summary (6 lines)

- What: Ship a small, reliable Hospital BI demo: SQLite schema, 10 KPI SQL + KPI Runner, 1‑page Power BI, Validation, Governance.

- Why: Faster, safer decisions with clear, reproducible metrics (Admissions, Avg LOS, Door‑to‑Doc, LWBS %, Payer Mix).

- Who: Sponsor (A), Ops Lead (R), BI Lead (R), Clinician (C), QA/UAT (R), Compliance (C), PM (I).

- When: V1 in 7 days; two 12‑min sprints/day; weekly review.

- How: Gate checks at each phase; artifact‑first communication.

- Done When: ERD.png, KPI_Runner.csv, PBIX screenshot, README, Validation checklist, RACI, this One‑Pager.

A) One‑Page Workflow (WWWWWH) with Gate Checklists Phase 0 — Intake & Scope (Why/What/Who/How)

- Risk → Control: Vague goals → 1‑sentence problem + 3 measurable outcomes.

- Why: 1‑sentence problem (e.g., reduce ED LWBS; improve Door‑to‑Doc P90)

- What: 3 goals; 10 KPIs; data sources; constraints

- Who: Exec Sponsor (Quality) A; Product Owner (ED/Ops) R; BI/Data; SMEs

- How: PHI minimum necessary; role‑based access; UAT sign‑off rule; success criteria

- When/Where: MVP date; sprint cadence; UAT window; envs (dev/test/prod) Gate 0 (Scope) — Do these 3

- Write the problem + 3 goals; confirm 10 KPIs.

- Log guardrails (PHI minimum necessary; UAT sign‑off rule).

- Record approvals: Sponsor + Product Owner. Artifacts to file (Gate 0): /docs/README.md (Scope), /docs/glossary.md (stub)

Phase 1 — Discovery & Definitions (Who/What/How)

- Risk → Control: Metric confusion → SME/HIM/Privacy review and versioned definitions.

- Who: Product Owner; Clinical SME (ED); HIM; Privacy/Compliance

- What: Glossary; KPI logic (denominators, inclusions/exclusions); source fields; business rules

- How: Data dictionary; ERD concept; mock KPI cards Gate 1 (Definitions) — Do these 3

- Draft glossary + KPI definitions; add data dictionary entries.

- Review with SME, HIM, Privacy; capture changes.

- Version the docs; record sign‑off. Artifacts to file (Gate 1): /docs/glossary.md, /docs/data_dictionary.md, /docs/img/erd_concept.png

Phase 2 — Model & Build (How/Where/When)

- Risk → Control: Access or model gaps → Tech/Sec review before UAT.

- How: Logical model → ERD → DDL; CSV→SQLite; BI semantic model; PBIX draft

- Where: Dev/test; access controls; audit logs

- When: Sprint plan; definition of done per story Gate 2 (Tech/Sec) — Do these 3

- Export ERD (PNG) + DDL; load CSVs to SQLite; run 10 KPI queries.

- Build PBIX: Calendar table, relationships, _Measures, slicers + 4 cards + matrix + trend.

- Review access with InfoSec/Privacy; record approvals. Artifacts to file (Gate 2): /docs/img/erd.png, /sql/*.sql, /artifacts/HospitalBI.pbix, /docs/img/pbix_mock.png

Phase 3 — UAT & Training (Who/How/When)

- Risk → Control: Hidden defects → Trace tests to acceptance criteria.

- Who: Product Owner A (UAT lead); end‑users (nurses/flow/bed mgmt); BI

- How: Test cases from acceptance criteria; defects tracked; quick ref card

- When: UAT window; go/no‑go Gate 3 (Go‑Live) — Do these 3

- Run UAT; log defects; retest until pass.

- Publish quick reference (definitions, slicer rules).

- Record Product Owner + Sponsor go‑live approvals. Artifacts to file (Gate 3): /docs/uat_plan.md, /docs/quick_ref_card.pdf, approvals record

Phase 4 — Go‑Live & Hypercare (Where/When/How)

- Risk → Control: Breakage post‑launch → Daily checks + rollback plan.

- Where: Production; refresh schedules; data SLAs

- When: 1–2 weeks hypercare; on‑call; daily metric check

- How: Rollback plan; change log; usage telemetry; incident path Gate 4 (Hypercare Exit) — Do these 3

- Monitor daily: cards render; refresh ok; KPI sanity.

- Close or backlog open issues; capture one success story.

- Transition ownership to BAU; record exit approval. Artifacts to file (Gate 4): /docs/change_log.md, /docs/success_story.md

Phase 5 — BAU & Improve (Why/What/Who)

- Risk → Control: Stagnation → Quarterly reviews + curated backlog.

- Why: Tie KPIs to unit huddles; quarterly reviews

- What: Improvement backlog; deprecation policy

- Who: Product Owner curates; BI/Data sustain; Compliance oversight

B) Swimlane Visual (Roles vs Phases) — Plain Language Lanes: Sponsor | Product Owner (ED/Ops) | Clinical SME | HIM | Privacy/Compliance | IT/Data Eng | BI/Analytics | InfoSec | PM/Scrum

- 0: Sponsor A; Product Owner R; PM R

- 1: Product Owner R; SME C; HIM/Privacy C/A; PM R

- 2: IT/Data R; BI R; InfoSec/Privacy C; PM R

- 3: Product Owner A; SME C; BI R; HR/Training R; PM R

- 4: IT/Data R; BI R; Product Owner A; PM R

- 5: Product Owner A; BI/IT R Legend: A=Accountable; R=Responsible; C=Consulted; I=Informed

C) Prefilled RACI Matrix (Hospital Demo) (Use the legend: A=Accountable; R=Responsible; C=Consulted; I=Informed) Deliverables (rows) → Roles (columns)

- Business case & scope: A | R | C | I | I | I | I | I | R

- Glossary & KPI definitions: I | A | C | A | C | I | I | I | R

- Data model (ERD/DDL): I | C | I | I | C | R | C | C | R

- Ingest/ETL jobs: I | C | I | I | C | R | I | C | R

- BI model & reports (PBIX): I | A | C | I | C | C | R | I | R

- UAT plan & sign‑off: I | A | C | I | I | I | I | I | R

- Training & comms: I | C | I | I | I | I | I | I | R

- Security & access: I | C | I | I | A | C | C | R | R

- Go‑Live runbook: I | A | C | I | C | R | R | C | R

- Compliance packet: I | C | I | A | A | I | I | I | R

D) Acceptance Criteria → UAT (map)

- Formula/rounding/exclusions → sample‑to‑report tie‑out

- Access roles → role‑based view checks

- Performance (<10s open) → timed open/export

- Export available → CSV download & re‑calc

E) Communications (Do not skip)

- Kickoff (Scope + guardrails) → Gate 1 review → Gate 2 Tech/Sec review → UAT invite/schedule → Go‑live note + hypercare contacts → Success story (artifact + one metric win)

F) Approvals Record Strip

- Gate 0 (Scope): Exec Sponsor ____ | Product Owner ____ | Date ____

- Gate 1 (Definitions): Product Owner ____ | SME ____ | HIM ____ | Privacy ____ | Date ____

- Gate 2 (Tech/Sec): IT/Data ____ | InfoSec ____ | Privacy ____ | Date ____

- Gate 3 (Go‑Live): Product Owner ____ | Exec Sponsor ____ | Date ____

- Gate 4 (Hypercare Exit): Product Owner ____ | BI/Data ____ | Ops Leader ____ | Date ____

Appendix — Concrete Mapping to Your Demo

- KPI set (5 core): Admissions (DISTINCT admission_id), Avg LOS (days excl active), LWBS % (ed_visits.dispo='LWBS'), Avg Door‑to‑Doc (min), Payer Mix (% by admissions.payer)

- SQL Pack: /sql/kpi_*.sql + /sql/kpi_runner.sql → export to /artifacts/kpi_runner.csv

- ERD: /docs/img/erd.png; DDL in /sql/ (SQLite)

- PBIX (model): Calendar table marked as date; relationships: Calendar[Date]→admissions[AdmitDate], Calendar[Date]→ed_visits[ArrivalDate]; _Measures table; 4 KPI cards; Date slicer (Between); Dispo slicer (Dropdown); Payer Mix matrix (% of column total); Admissions trend line

- Slicer behavior: Date filters all visuals; Dispo filters ED visuals only (LWBS %, Door‑to‑Doc, Dispo matrix)

- Validation: /docs/validation_checklist.md (row counts; null/date sanity; LOS non‑negative; payer mix ~100%; reproducibility)

- Governance artifacts: /artifacts/raci.csv; this one‑pager (PDF); Approvals Record completed