Title: RACI + WWWWWH Visuals (Quick Map)

A) Phase Map with Gates (ASCII)

[Phase 0] Intake & Scope --Gate 0--> [Phase 1] Discovery & Definitions --Gate 1--> [Phase 2] Model & Build --Gate 2--> [Phase 3] UAT & Training --Gate 3--> [Phase 4] Go-Live & Hypercare --Gate 4--> [Phase 5] BAU

Gate 0: Sponsor approves WHY/WHAT/WHO/HOW guardrails Gate 1: SMEs/HIM/Privacy sign off glossary + KPI definitions Gate 2: IT/Data + Security review access/architecture Gate 3: Product Owner/Sponsor go-live approval after UAT pass Gate 4: Hypercare exit; move to steady-state

B) WWWWWH Swimlane (Roles vs Phases)

Lanes: Sponsor | Product Owner | Clinical SME | HIM | Privacy/Sec | IT/Data | BI | PM/Scrum

Phase 0 (Intake)

- Sponsor: Approve problem/goals (A)

- Product Owner: Draft scope + success criteria (R)

- PM: Kickoff, RACI draft, timeline (R)

Phase 1 (Discovery)

- Product Owner: Run SME workshops (R)

- Clinical SME: Define metric logic, edge cases (C)

- HIM: Validate definitions/retention (C/A)

- Privacy/Sec: Minimum necessary rules (C/A)

- PM: Gate 1 sign-off (R)

Phase 2 (Model/Build)

- IT/Data: ERD/DDL/ETL (R)

- BI: Model + dashboard draft (R)

- Privacy/Sec: Access roles (C/A)

- PM: Gate 2 review (R)

Phase 3 (UAT/Training)

- Product Owner: UAT plan + testers (A)

- Clinical SME: Execute test cases (C)

- BI: Fixes (R)

- HR/Training: Quick references (R)

- PM: Gate 3 go/no-go (R)

Phase 4 (Go-Live/Hypercare)

- IT/Data: Prod cutover (R)

- BI: Monitor performance/errors (R)

- Product Owner: Daily huddle checks (A)

- PM: Gate 4 exit (R)

Phase 5 (BAU)

- Product Owner: Backlog grooming (A)

- BI/IT: Sustain + small releases (R)

C) Acceptance Criteria → UAT Mapping

- AC: KPI formula, rounding, exclusions → UAT: sample-to-report tie-out

- AC: access roles → UAT: role-based checks (can/can’t see)

- AC: performance (<10s) → UAT: timed open/export

- AC: export CSV available → UAT: download and re-calc

D) Sample RACI Snapshot (One Deliverable) Deliverable: BI model & reports

- Sponsor: I

- Product Owner: A

- Clinical SME: C

- HIM: I

- Privacy/Sec: C

- IT/Data Eng: C

- BI Dev/Analyst: R

- InfoSec: I

- PM/Scrum: R

E) Communications Points (Don’t Skip)

- Kickoff (Scope + guardrails)

- Definitions review (Gate 1)

- Tech/Sec review (Gate 2)

- UAT invite + schedule (Gate 3 prep)

- Go-live note + hypercare contacts

- Success story (artifact + one metric win)