## RACI Matrix
Deliverable | Exec Sponsor | Product Owner (Ops/Quality) | Clinical SME (ED/Bed) | HIM | Privacy/Security | Legal | IT/Data Eng | BI Dev/Analyst | InfoSec | PM/Scrum | HR/Training | Comms/Marketing | Informed Stakeholders
Business case & scope | A | R | C | I | I | C | I | I | I | R | I | I | I
Glossary & KPI definitions | I | A | C | A | C | I | I | I | I | R | I | I | I
Data model (ERD/DDL) | I | C | I | I | C | I | R | C | C | R | I | I | I
Ingest/ETL jobs | I | C | I | I | C | I | R | I | C | R | I | I | I
BI model & reports | I | A | C | I | C | I | C | R | I | R | I | I | I
UAT plan & sign-off | I | A | C | I | I | I | I | I | I | R | C | I | I
Training & comms | I | C | I | I | I | I | I | I | I | R | R | C | I
Security & access | I | C | I | I | A | C | C | I | R | R | I | I | I
Go-Live runbook | I | A | C | I | C | I | R | R | C | R | I | I | I
Compliance packet (HIPAA/CMS/DC/AHIMA/TJC) | I | C | I | A | A | C | I | I | I | R | I | I | I

## Legend
Role | Color
R (Responsible) | Red
A (Accountable) | Green
C (Consulted) | Blue
I (Informed) | Yellow

## Summary
Role | R | A | C | I | Role (Description)
Exec Sponsor | 0 | 1 | 0 | 9 | Exec Sponsor (Executive Sponsor)
Product Owner (Ops/Quality) | 1 | 4 | 5 | 0 | Product Owner (Ops/Quality) (Oversees Ops/Quality)
Clinical SME (ED/Bed) | 0 | 0 | 5 | 5 | Clinical SME (ED/Bed) (Clinical Subject Matter Expert)
HIM | 0 | 2 | 0 | 8 | HIM (Health Information Management)
Privacy/Security | 0 | 2 | 5 | 3 | Privacy/Security (Privacy & Security Compliance)
Legal | 0 | 0 | 3 | 7 | Legal (Legal Advisor)
IT/Data Eng | 3 | 0 | 2 | 5 | IT/Data Eng (IT & Data Engineering)
BI Dev/Analyst | 2 | 0 | 1 | 7 | BI Dev/Analyst (Business Intelligence Developer/Analyst)
InfoSec | 1 | 0 | 3 | 6 | InfoSec (Information Security)
PM/Scrum | 10 | 0 | 0 | 0 | PM/Scrum (Project Manager / Scrum Master)
HR/Training | 1 | 0 | 1 | 8 | HR/Training (Human Resources & Training)
Comms/Marketing | 0 | 0 | 1 | 9 | Comms/Marketing (Communications & Marketing)
Informed Stakeholders | 0 | 0 | 0 | 10 | Informed Stakeholders (General Stakeholders)