Title: RACI + Workflow Kit (Hospital BI Project)

Purpose A simple, repeatable way to involve the right people (RACI) and move work through clear gates (Who/What/When/Where/Why/How = WWWWWH), so you don’t skip approvals, reviews, or comms.

A) One‑page Workflow (WWWWWH) Phase 0 — Intake & Scope (Why/What/Who)

- Why: State the problem in one sentence (e.g., reduce ED LWBS; improve Door‑to‑Doc P90).

- What (outcomes): 3 measurable goals; 10 KPIs list; data sources; constraints.

- Who: Name Sponsor (A), Product Owner (Ops/Quality), Data/BI leads (R), SMEs (C).

- When: Target MVP date; sprint cadence; UAT window.

- Where: System scope (ED, inpatient, finance); environments (dev/test/prod).

- How (guardrails): PHI handling, minimum necessary, UAT sign‑off rule, success criteria. Gate 0 checklist (Sponsor approves problem, scope, goals, guardrails).

Phase 1 — Discovery & Definitions (Who/What/How)

- Who: SMEs (ED charge nurse/bed czar), HIM, Privacy/Security, IT.

- What: Metric definitions (e.g., LWBS denominator), source tables/fields, business rules.

- How: Glossary, data dictionary, ERD concept, mock KPIs.

- When/Where: 1–2 workshops; record in SharePoint/Trello cards. Gate 1 checklist (Glossary + data dictionary reviewed by SMEs and HIM/Privacy).

Phase 2 — Model & Build (How/Where/When)

- How: Logical model → ERD → DDL; ETL/ingest; BI semantic model; dashboard draft.

- Where: Dev/test environment; access controls; audit logs.

- When: Sprint plan; “definition of done” per story. Gate 2 checklist (Tech review by IT/Data; Privacy/Security sign‑off on access).

Phase 3 — UAT & Training (Who/How/When)

- Who: UAT lead from Ops/Quality; end‑users (nurses/flows/bed mgrs).

- How: Test cases from acceptance criteria; defects tracked; training plan; quick‑ref cards.

- When: UAT window + go/no‑go meeting. Gate 3 checklist (UAT pass + Sponsor go‑live approval).

Phase 4 — Go‑Live & Hypercare (Where/When/How)

- Where: Production; refresh schedules; data SLAs.

- When: 1–2 weeks hypercare; daily metrics check; on‑call contact.

- How: Rollback plan; change log; usage telemetry; incident path. Gate 4 checklist (Hypercare exit; move to BAU).

Phase 5 — BAU & Improve (Why/What/Who)

- Why: Tie KPIs to unit huddles; quarterly review.

- What: Backlog of improvements; deprecation policy.

- Who: Product Owner curates backlog; BI/Data sustain; Compliance oversight.

B) RACI Matrix (Template) Deliverables (rows)

- Business case & scope

- Glossary & KPI definitions

- Data model (ERD/DDL)

- Ingest/ETL jobs

- BI model & reports

- UAT plan & sign‑off

- Training & comms

- Security & access

- Go‑Live runbook

- Compliance packet (HIPAA/CMS/DC/AHIMA/TJC pointers)

Roles (columns)

- Executive Sponsor (A)

- Product Owner (Ops/Quality) (A/R)

- Clinical SME (charge nurse/bed czar) (C)

- HIM (C/A for definitions/retention)

- Privacy/Security (C/A for access)

- Legal (C when data sharing/BAA/retention policy changes)

- IT/Data Eng (R)

- BI Dev/Analyst (R)

- InfoSec (C)

- PM/Scrum (R)

- HR/Training/Change (C/R for training)

- Comms/Marketing (C if external)

RACI Legend R = Responsible (does the work) | A = Accountable (final sign‑off) | C = Consulted | I = Informed

C) Gate Checklists (copy/paste to cards) Gate 0 — Sponsor approval (problem/goals/guardrails) Gate 1 — Glossary/data dictionary reviewed (SME/HIM/Privacy) Gate 2 — Tech & Security review (IT/Data; Privacy/Sec) Gate 3 — UAT pass + go‑live approval (Sponsor/Product Owner) Gate 4 — Hypercare exit to BAU (Ops/BI/Data)

D) Acceptance Criteria (turn into UAT cases)

- Metric formulas (with inclusions/exclusions and rounding).

- Data refresh cadence; latency; export options.

- Performance (e.g., dashboard < 10s; export < 10s).

- Access roles (min necessary; audit trail on).

- Validation checks (sample‑to‑report tie‑outs).

E) Status & Backlog Boards (simple structure) Columns: Now / Next / Sandbox / Parked | Card: Story, AC, Owner, Estimate, Due, Gate, Risks, Links.

F) Communications Plan (one‑page)

- Kickoff: Sponsor + team

- SME workshops (Discovery)

- UAT schedule

- Go‑live announcement (internal)

- Success story + lessons learned

G) Approvals Record (one‑liners)

- Gate 0: Sponsor (name/date)

- Gate 1: SME/HIM/Privacy (names/dates)

- Gate 2: IT/Data/InfoSec (names/dates)

- Gate 3: Product Owner/Sponsor (names/dates)

- Gate 4: Ops/BI/Data (names/dates)

Usage

- Keep this doc in the project root; link it on the top of the tracking board.

- Each deliverable row in RACI must have at least one R and exactly one A.

- Don’t pass a gate without named approvals.